## Sheet1
Defect ID | Test Case ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Status
DEF-01 | TC-01 | Category filter (Phones, Laptops, Monitors) does not update product listing | 1. Go to homepage 2. Click “Phones” under CATEGORIES 3. Observe product list | Only phone products (e.g., Samsung Galaxy S6, iPhone 6) are displayed | Product list remains unchanged; all products (phones, laptops, monitors) still visible | High | Open
DEF-02 | TC-03 | Misleading error message when Name field is empty | 1. Add item to cart 2. Click “Place Order” 3. Leave Name empty, fill Credit Card 4. Click “Purchase” | Alert: “Please fill out Name.” | Alert: “Please fill out Name and Credit Card.” | Medium | Open
DEF-03 | TC-04 | Cart does not consolidate duplicate products | 1. Add “Samsung Galaxy S6” to cart 2. Add it again 3. Open Cart | One entry: “Samsung Galaxy S6”, quantity = 2, total = 720 | Two separate entries of “Samsung Galaxy S6” (360 each) | Medium | Open